## Slide 1
SMU STUDENT STARTUP
Business Plan
Competition
2027
Applications Open
1 Jan 2027
Applications Close
31 Mar 2027
Results Announced
30 Jun 2027
Organized by Singapore Management University

## Slide 2
OVERVIEW
About This Competition
100
Finalist
Startups
10
Expert
Judges
10
Winners
Selected
3
Months for
Applications
Eligibility
University students (undergraduate, postgraduate, doctoral) from any country
Recent alumni who graduated within the last 5 years
Teams of up to 5 members — at least 1 must be the lead founder

## Slide 3
STRUCTURE
Five Core Operational Tasks
1
Sourcing participants
Attract 300–500 global applicants to select 100 finalists
→
2
Sourcing judges
Identify and invite 25–30 candidates to confirm 10 experts
→
3
Matching judges to participants
Domain-aligned, conflict-free assignment with workload balance
→
4
Evaluating pitch decks
Structured async scoring using a 100-point rubric
→
5
Choosing the top 10 winners
Quantitative ranking + deliberation panel + secret ballot
→
Each task is presented in two parts:
Part A: Human approach
Part B: Agentic AI approach

## Slide 4
1
TASK 1
Sourcing Startup Participants
Attracting 300–500 global applicants to select 100 finalists

## Slide 5
TASK 1 · PART A
Human Approach: Sourcing Participants
University networks
Email entrepreneurship & innovation office directors at 200 target universities. Provide a ready-to-use promo kit: one-pager, email template, social copy, poster.
Startup ecosystem
Reach out to BLOCK71, Antler, SGInnovate, Y Combinator Startup School, Techstars, and regional hubs in Jakarta, Bangalore, Lagos & São Paulo.
Digital & social
LinkedIn groups, Reddit, F6S, Startup Digest, and regional Telegram channels. Optional paid ads on LinkedIn (budget: S$3–8K) targeting student founders.
Student ambassadors
Recruit 10–15 ambassadors from key universities. Each runs a campus info session and recruits peers via personal referral link.
⚑ Guardrail Unique referral codes track each channel's conversion. Operations manager reviews application pace weekly and redirects effort if any channel underperforms.

## Slide 6
TASK 1 · PART B
Agentic AI Approach: Sourcing Participants
Research
Agent
→
Outreach
Agent
→
Human
Approval
→
Pipeline
Monitor
AI Agent
University prospect finder
Crawls 200 university portals, extracts contact names & emails, ranks by QS ranking and known startup activity. Output: structured spreadsheet ready for outreach.
AI Agent
Personalised email drafter
Generates tailored invitation emails per contact — personalised by university name and startup focus. Flags uncertain cases for human review before any send.
AI Agent
Social listening agent
Monitors LinkedIn and X for student founders who haven't applied yet. Drafts a DM template for human review — never sends autonomously.
Automated
Eligibility pre-screener
On each submission, auto-checks student status, documents, and team size. Auto-rejects ineligible applications; flags edge cases for human review within 48 hrs.
⚑ Guardrail No outreach email is sent without explicit human approval. ~120 staff-hours saved vs manual across the 3-month application window.

## Slide 7
2
TASK 2
Sourcing & Inviting Judges
Confirm 10 judges by inviting 25–30 candidates. Start September 2026.

## Slide 8
TASK 2 · PART A
Human Approach: Sourcing Judges
VCs & Investors
4–5 slots
Partners at SEA-focused funds: Sequoia SEA, Monk's Hill, Wavemaker, East Ventures. Angel investors and family office principals.
Corporate Leaders
3–4 slots
CTOs & Chief Innovation Officers at MNCs with Singapore presence. Source from SMU IIE's existing corporate partner list first.
Successful Founders
2–3 slots
Founders who raised Series A+, exited, or scaled regionally. SMU alumni founders are highest-priority — most likely to accept.
Academics & Policy
1–2 slots
SMU/NUS professors with entrepreneurship expertise. Optional: 1 government representative from EDB, A*STAR, or SGInnovate.
Invitation cadence:
Wave 1 (Sep 2026): 15 candidates on SMU letterhead, signed by the Dean
Wave 2 (Oct 2026): 10 more if fewer than 8 have accepted
Wave 3 (Nov 2026): Fill remaining slots from reserve list
⚑ Guardrail Maintain a reserve list of 5 backup judges. Even confirmed judges cancel. Aim for ≥40% women and ≥5 nationalities on the panel.

## Slide 9
TASK 2 · PART B
Agentic AI Approach: Sourcing Judges
AI Agent
Judge candidate researcher
Searches LinkedIn, Crunchbase & conference speaker lists. Scores 30 candidates 1–10 for relevance across the 4 judge profiles.
AI Agent
Invitation letter drafter
Composes personalised letters with the candidate's specific expertise and time commitment stated precisely. Draft sent to human for approval before any letter is dispatched.
Automated
Follow-up scheduler
Day 10: auto follow-up email. Day 20: flags for personal LinkedIn message. After 2 no-responses: advances next candidate on reserve list.
AI Agent
Diversity gap analyser
Tracks gender, nationality & domain coverage in real time. Flags imbalances and suggests specific reserve candidates to improve panel balance.
Automated
Onboarding dispatcher
On acceptance: auto-sends NDA (DocuSign), calendar invite, portal login, and briefing PDF. Zero manual coordination for paperwork.
⚑ Guardrail No invitation letter is sent without explicit human approval. The AI researches and drafts — humans decide who to invite and when.

## Slide 10
3
TASK 3
Matching Judges to Participants
Domain-aligned, conflict-free assignment with balanced workloads

## Slide 11
TASK 3 · PART A
Human Approach: Matching Judges
1
Tag all 100 startups
Assign up to 3 sector tags from a fixed taxonomy: HealthTech, CleanEnergy, AgriTech, EdTech, FinTech, MobilityTech, DeepTech, B2B SaaS, Social Impact.
2
Tag all judges
Map each of the 10 judges to 2–3 domain expertise areas using the same taxonomy. Note preferred load (10 or 20 decks).
3
Group into 10 panels
Cluster 100 startups into 10 panels of 10, grouped by shared sector tag. Assign a primary (domain-matched) + secondary (generalist) judge to each.
4
Run conflict-of-interest check
Send judges the finalist list. Ask them to flag any investment, advisory role, or personal connection. Reassign flagged startups to an alternate judge.
5
Freeze & activate
Chief judge approves the matrix. Judge portals are activated with only their assigned decks visible. Each judge receives a personalised assignment email.
⚑ Guardrail Overflow: If 30+ startups share one sector but only 1 judge has expertise, distribute the overflow to generalist judges with a one-page sector guide.

## Slide 12
TASK 3 · PART B
Agentic AI Approach: Matching Judges
AI Agent
Pitch deck sector tagger
Reads all 100 decks. Extracts problem statement, solution & target market. Assigns sector tags with confidence scores. Flags <70% confidence for human review.
AI Agent
Conflict-of-interest detector
Fetches each judge's portfolio (Crunchbase) and advisory roles (LinkedIn). Produces a 10×100 conflict matrix: 'clear', 'potential conflict', or 'flagged'.
AI Agent
Matching optimiser
Constraint-satisfaction algorithm: maximise domain match, ensure 2 judges per startup, eliminate conflicts, balance load (8–22 decks each). Runs in under 2 hours.
Automated
Portal access provisioner
On human approval: automatically unlocks each judge's portal with only their assigned decks. Sends personalised email with assignment list and 4-week deadline.
⏱ Time saving:
What takes a human 2–3 days of spreadsheet work (tagging 100 decks, conflict checks, load balancing) takes the agentic system under 2 hours — with a cleaner audit trail.
⚑ Guardrail The matching matrix is never activated automatically. Chief judge must explicitly approve after reviewing conflict, match score, and diversity reports.

## Slide 13
4
TASK 4
Evaluating Pitch Decks
4-week async scoring window · 100-point rubric · dual independent judges

## Slide 14
TASK 4 · PART A
Human Approach: Evaluating Pitch Decks
Criterion
Weight
Visual weight
Problem & market
20%
Solution & innovation
25%
Business model
20%
Traction & validation
15%
Team
15%
Pitch quality
5%
Calibration session
60-min Zoom briefing for judges before scoring begins. Walk through rubric + 3 anonymised sample decks at different quality tiers.
Async scoring window
4 weeks (Apr–May 2027). Each judge reviews 10–20 decks at ~12–15 min each. Mandatory comment per criterion.
Progress tracking
Operations lead monitors completion weekly. Reminders at week 2; escalation at week 3 if below 70% complete.
Anomaly review
If two judges' scores on the same startup differ by >15 points, the chief judge reviews both scoresheets.
⚑ Guardrail Judges score 1–5 per criterion independently. They cannot see each other's scores until deliberation.

## Slide 15
TASK 4 · PART B
Agentic AI Approach: Evaluating Pitch Decks
AI Agent
Deck summariser
Generates a 1-page structured summary per deck: problem, solution, market, business model, traction, team. Labelled 'AI-generated — for orientation only'. Cuts judge prep time from ~5 min to ~1 min per deck.
AI Agent
Scoring anomaly detector
After all scores submitted: (1) inter-rater gap >15 pts flagged; (2) score compression (range <20 pts) flagged; (3) statistical outliers in top/bottom 5% reported. All sent to chief judge.
Automated
Judge progress tracker
Weekly completion reports per judge. Auto-reminder at week 2 if below 50%. Personal escalation at week 3 if below 70%. Routes unfinished decks to reserve judge at close.
AI Agent
Feedback quality reviewer
Checks each comment field: minimum 10 words, must reference something specific. Prompts judge to elaborate before submission is accepted — protecting feedback quality for all 100 finalists.
AI Agent
Score normalisation engine
If systematic bias detected, optionally applies per-judge z-score normalisation. Shows original AND adjusted scores to chief judge for explicit approval or rejection before rankings run.
⚑ Guardrail CRITICAL: The AI never scores a pitch deck. Scores 1–5 per criterion are entered exclusively by human judges. This rule is enforced at the portal level.

## Slide 16
5
TASK 5
Choosing the Top 10 Winners
Quantitative ranking + deliberation panel + secret ballot → results 30 Jun 2027

## Slide 17
TASK 5 · PART A
Human Approach: Selecting Winners
Stage A — Score-ranked longlist
Compute weighted average from dual-judge scores for all 100 startups
Rank from highest to lowest — top 20 advance to shortlist
Diversity scan: check if top 20 is skewed by sector, region, or university
If score tie at 20/21, both teams advance (temporary shortlist of 21)
Stage B — Deliberation panel
3-hour virtual or in-person session chaired by the chief judge
Champion/challenge format: 2 min to advocate, 1 min to challenge per team
Secret simultaneous ballot — teams with 6+ votes confirmed
Chief judge holds casting vote for unresolvable ties
Winners notified privately 5 days before the 30 Jun public announcement
Prize structure
Champion (1st)
Cash prize + SMU accelerator + mentorship + trophy
Excellence (2nd & 3rd)
Cash prizes + co-working credits + investor intros
Top 10 recognition
Certificate + website feature + network access
Category awards
Best Social Impact, Best DeepTech, People's Choice
⚑ Guardrail Announce all 100 finalists publicly on 30 Jun 2027 alongside the top 10 — every finalist gains a prestigious credential regardless of final ranking.

## Slide 18
TASK 5 · PART B
Agentic AI Approach: Selecting Winners
AI Agent
Ranking & shortlist engine
Computes weighted averages, applies approved normalisation, produces ranked leaderboard and top-20 shortlist with per-criterion score breakdown PDFs.
AI Agent
Deliberation brief writer
1-page brief per top-20 team: strongest/weakest criteria, key judge comment quotes, how the team compares to similar startups in the pool.
AI Agent
Diversity & balance analyser
Analyses top 20 across sector, geography, university tier & gender. Reports imbalances to chief judge before deliberation — an informed choice, not a blind one.
Automated
Winner comms bundle
Auto-generates winner notification emails, press release draft, website copy, and LinkedIn/X posts in 3 tones. All require director sign-off before any are sent.
Automated
Feedback report generator
For all 100 finalists: personalised report with per-criterion scores, anonymised judge comments, and relative pool ranking. Distributed on announcement day.
⚑ Guardrail CRITICAL: The final top-10 decision is made exclusively by judges via secret ballot. AI ranks and briefs — it never recommends who should win.

## Slide 19
AI GOVERNANCE
Agentic AI Guardrail Summary
AI must NEVER
Never sends outreach emails or invitations autonomously
Never scores a pitch deck — scoring is exclusively a human function
Never activates the judge-participant matching matrix without chief judge approval
Never recommends who the top 10 winners should be
Never sends winner notifications or press releases without director sign-off
AI may autonomously
Auto-screen clearly eligible or ineligible applications
Send automated progress reminders to judges mid-scoring window
Generate feedback reports for all 100 finalists after results are confirmed
Produce weekly application pace reports and channel performance dashboards
Draft outreach copy, letters, and comms bundles — all pending human approval
Core principle:
AI handles research, drafting, tracking, and computation. All consequential decisions — who to invite, who wins, what to send — remain with human organizers and judges.

## Slide 20
Ready to launch
SMU Student Startup
Competition 2027
100
Global finalists
10
Expert judges
5
AI-augmented tasks
Singapore Management University · Applications open 1 January 2027